## Sheet1
MONTH | ASSESSMENT | TASK | DONE
JULY |  | Update school contacts (Sup/Prin/DAC/NTAC/TAC) with the Assessment Office | q
| ELPA | Redesignate proficient EL students in district SIS | q
| NAEP | Districts will be notified of schools selected to participate in testing | q
AUGUST | ELPA | Update TIDE district and building users | q
| NAEP | Participating districts must complete the Technology Survey | q
| Districts | Download final student data files/reports from previous spring posted in the appropriate vendor systems | q
| MAP Growth | MAP Growth Fall Test Window for grades 3-8 (Testing optional for districts) | q
SEPTEMBER | NDE/Districts | Sign Principal and DAC Security Agreements | q
| ACT | ACT Online Prep opens | q
| ACT | Accommodations and EL Supports Training Session | q
| ACT | Accommodations and EL Supports window opens in TAA for spring testing | q
| PreACT | Training Webinar | q
OCTOBER | NDE | Assessment Fall Roadshows | q
| NSCAS ALT | 1% Threshold Justification Submission | q
| ELPA | Preliminary window to order paper, large print, Braille versions | q
| ACT | Pre-Roster Data Verification - review and edit roster through ADVISER | q
| PreACT | Fall test window begins | q
NOVEMBER | ACT | Confirm Participation and Select Test Event | q
| ACT | Review Student Rosters in ACT Now | q
| NDE | NEP released to public | q
DECEMBER | NSCAS ALT & ELPA | Pre-Roster Data Verification - review and edit rosters through ADVISER | q
| ACT | Test Admin Training Sessions Part 1 & 2 | q
| Districts | Districts conduct Test Security training & submit completed District & Staff Security Agreements | q
| Districts | Last chance to download previous year's student results files/reports before they are removed from the vendor's testing systems | q
| MAP Growth | MAP Growth Winter Test Window for grades 3-8 (Testing optional for districts) | q
JANUARY | ELPA | Place order for additional paper, large print, Braille versions | q
| ELPA | ELPA21 & Alt ELPA: Testing Window begins and runs through March (Mandated testing) | q
| NAEP | Testing Window Begins and runs through March | q
FEBRUARY | NSCAS GEN | Pre-Test Verification review | q
| NSCAS GEN & ALT | Test Administration Q&A | q
| ACT | Accommodations window closes for initial requests for spring testing Qualified Exceptions to Accommodations deadlines can be requested | q
| ACT | Submit late enrollment records in ACT Now (no bar codes) | q
| ACT | Create test sessions in TCM | q
| PreACT | Training Webinar | q
MARCH | NSCAS GEN & ALT | Test Management Opens (review roster, add accommodations, order paper/pencil, print tickets) | q
| NSCAS GEN & ALT | Test Window Opens and runs through May (Mandated testing) | q
| ELPA | Enter Reason Not Tested Codes in vendor system | q
| ACT | ACT Test Event #1 (Mandated testing) | q
| PreACT | Training Webinar | q
| PreACT | Spring test window begins | q
| MAP Growth | MAP Growth Spring Test Window for grades 3-8 (Testing optional for districts) | q
APRIL | ACT | ACT Test Event #2 (Mandated testing) | q
| ACT | ACT Test Event #3 (Make-up) | q
MAY | NDE/Districts | Post-test data verification reviews begin and run through August | q
| ELPA | Access summative scores in reporting section of NE portal | q
JUNE | MAP Growth | MAP Growth Summer Test Window for grades 3-8 (Testing optional for districts) | q